## Sheet1
Sl. No. | dept_no | Project Name: | Scope of Work: | Funding Agency/ Mode | Budget Head: | Agency Name with WO Details: | Estimated Cost: | Awarded Cost: | Scheduled Date of Completion(as per WO): | Project Licence Validity: | Project Manager: | Contact No of Project Manager: | WORK TYPE | ZONE | DIVISION
1 |  | (A) Construction of 2X160 MVA, (220/132/33Kv) & 2x40MVA, (132/33kv) 220/132/33Kv Grid S/S at Pratapsasan, (B) 02 nos. 220kv Bay extension at Nuapada S/S, (C) 2 nos. 132kv Bay extension at Phulnakhara S/S (D) Aassociated 220kv DC transmission line on 220kv DC tower from Nuapada (Cuttack) to proposed Pratapsasan S/S (32.267Kms. Approx.) (E) 132 KV DC circuit transmission lines on 132 KV DC tower from proposed Pratapsasan S/S to132/33KV S/S at Phulnakhara. (Line length:14.75Kms) | Substation: TFR Capacity: 220/132KV - 2x160MVA 132/33 KV – 2X40MVA 220KV bay - 7 nos. 132KV bay - 9 nos. 33 KV bay - 8 nos Line : 220KV DC line(revised) -48.12Km 132 KV DC LILO Line – 15.038 Kms. | SCRIPS | NULL | Original work order placed with M/s. LANCO Infratech Ltd., W.O. No.4980 dt.18.06.13 (Supply) & No: 4985 dt.18.06.13 (Erection). Order placed after offloading of the work with the followings: 1.Construction of balance work of 220/132/33kV sub-station Pratapsasan: M/s Empower Bhubaneswar, NOA No. 2477 dt.21.05.2018. 2. Construction of balance work of 220 kV D/C line from Nuapada to Pratapsasan: M/S A.K.Das Associates Ltd, NOA no.5177 dtd.10.10.2018 3. Construction of 220 kV DC line from Loc No.50 to 102- 5nos rate contract holders of OPTCL. 4. Construction of balance work of 132kV D/C line from Phulnakhara to Pratapsasan: M/S Bharati Constructions.LOA No.3789 dtd.17.11.2017 | 105.47 | A),B) & C) S/S: 38.25 Supply=23.28 Erection=14.97 D)220kV Line: 2.68+31.2 Supply=15.26 Erection=18.61 E) 132kV Line: 1.46 Total Amt:73.59 Cr. | A)S/S :May-2019 B) 220kV Line: April-2020 D) 132kV Line: May 2018 | A),B)&C)30.06.2021 D)Applied up to 28.02.2022 |  |  | 1 | 1 | 2
2 |  | Constn. of 220KV Double Circuit Transmission line on DC tower from 400/220KV Grid S/S, Pandiabil (Benapanjari) of PGCIL to 220/132/33KV Grid Sub-station, Pratapasasan (Approx.Line Length: 30.636Km) on Turnkey basis. | Line : 220 KV DC Line –29.839 Kms. (No. of locations – 108) | DRPS | NULL | M/s Fedderes Lloyd Corpn.Ltd. Work orders: 9551 & 9556 dtd.22.09.2015 Contract Price: Erection-15,41,38,147/- & Supply – Rs.22,23,63,092/-. Contract terminated & new agencies engaged 1)M/s Lakheswar Electrical & Construction(from loc no: 45 to Gantry of Pratapsasan vide W.o no: 3038 dated 26.12.2018) 2)M/s Aay Bee Electrical & Construction(from loc no: 20 to 45 vide w.o no: 3039 dated 26.12.2018 3)M/s Mother Power House Pvt. Ltd.(Gantry of Pandiabil to loc no:20) vide W.o no:3040 dated 26.12.2018 | 29.15 | 29.308 | (Original schedule date ) Sept.-2017 Revised schedule date: April.-2019 | 'NA |  |  | 1 | 1 | 2
3 |  | 2X63MVA, 220/33kV Gas Insulated Sub-station at Godisahi (SCRIPS) | 220kV bay-05, 33kV bay-10 | SCRIPS | NULL | M/S Toshiba Transmission & Distribution System(India) Pvt. Ltd. W.O No. 118 dtd. 22.02.2019 | 68.39 | 95.34 Supply=72.05 Erection=23.29 | Aug.-2020 | '31.01.2022 |  |  | 1 | 1 | 2
4 |  | 2X63MVA, 220/33kV Gas Insulated Sub-station at Kantabada (SCRIPS) | 220kV bay-05, 33kV bay-10 | SCRIPS | NULL | M/S Toshiba Transmission & Distribution System(India) Pvt. Ltd. W.O No. 118 dtd. 22.02.2019 | 68.92 | 95.34 Supply=72.05 Erection=23.29 | Aug.-2020 | '31.01.2022 |  |  | 1 | 1 | 2
5 |  | 2X63MVA, 132/33kV Gas Insulated Sub-station at Satyanagar, BBSR (SCRIPS) | 132kV bay-07, 33kV bay-10 132kV UG cabling-Gangua to Satyanagar-5.3K.Ms 132kV UG cabling Gangua to Mancheswar-B-2.2K.Ms 132kV UG cabling-Mancheswar-B to Satyanagar-6K.Ms 132kV UG cabling-Unit-VIII to Satyanagar-3.672K.Ms | SCRIPS | NULL | M/S Sterlite Power Transmission Ltd JV with M/S MAVIN Switchgears & Control Pvt. Ltd. W.O No. 114 dtd. 22.02.2019 | 210.04 | 170.65 Supply=135.49 Erection=35.15 | Feb.-2021 | 'Applied but not availed yet. |  |  | 1 | 1 | 2
6 |  | 2X63MVA, 132/33kV Gas Insulated Sub-station at Badagada, BBSR (SCRIPS) | 132kV bay-07, 33kV bay-10 132kV UG cabling-Badagada to Satyanagar-6.5K.Ms 132kV UG cabling-Badagada-Kesura-6.65K.Ms | SCRIPS | NULL | M/S Sterlite Power Transmission Ltd JV with M/S MAVIN Switchgears & Control Pvt. Ltd. W.O No. 114 dtd. 22.02.2019 | 210.04 | 170.65 Supply=135.49 Erection=35.15 | Feb.-2021 | 'Applied but not availed yet. |  |  | 1 | 1 | 2
7 |  | 2X63MVA, 132/33kV Gas Insulated Sub-station at Nayapalli, BBSR (SCRIPS) | 132kV bay-07, 33kV bay-10 132kV UG cabling-Mancheswar AIS to Nayapalli-6.0K.Ms 132kV UG cabling-Unit-VIII to Nayapalli-6.0K.Ms 132kV UG cabling-Ekamra park to Nayapalli-3.0K.Ms 132kV AIS bay extension at Mancheswar AIS | SCRIPS | NULL | M/S A.K.Das Associates Ltd JV with M/S Cable Corporation of India Ltd. W.O No. 164 dtd. 07.03.2019 | 120.48 | 87.88 Supply=70.42 Erection=17.46 | 2020-09-01 | '30.09.2021 |  |  | 1 | 1 | 2
8 |  | 2X160MVA, 220/132kV & 2X63MVA 132/33kV, 220/132/33kV Gas Insulated Sub-station at Balianta(Benupur), BBSR with asscociated 220kV LILO O/H Transmission line(LILO on proposed 220kV DC line from Pratapsasan to Nuapada-Cuttack) using monopole & 132kV O/H Transmission line from Balianta GIS S/S up to Gangua Canal using 220kV DC monopole tower | 220kV Side: 220kV bays: 05 132kV Side: 132kV bays: 07 33kV Side: 33kV bays: 10 220kV O/H Line: 12K.Ms 132kV O/H Line: 08K.Ms | SCRIPS | NULL | M/S TATA PROJECTS LTD. W.O No: 174 dtd 08.03.2019 | 188.52 | 139.18 Supply=98.51 Erection=40.69 | 2020-09-01 | Applied but Not availed yet. |  |  | 1 | 1 | 2
9 |  | truction of 2X40MVA, 132/33kV Grid sub-station at Attoda, Bahugram with associated 132kV LILO line from 132kV ICCL-Salipur Line Ckt-I. | 132kV bay: 05 33kV bay: 08 132kV Line: 3.027K.Ms | JICA | NULL | M/s Siddhartha Engineering Ltd. W.O 1078 dtd. 08.03.2019. | 36.61 | 33.58 Supply=19.24 Erection=14.32 | May-2021 | 31.03.2022 |  |  | 1 | 1 | 1
10 |  | 2X40MVA, 220/33kV Grid sub-station, Palei, Balichandrapur with associated 220kV DC LILO line from 220kV New Duburi-Paradeep DC line Ckt-II. | 220kV Bay: 05 33kV Bay: 08 220kV bay: 2.0K.Ms | Own | NULL | M/s Blue Star Ltd. W.O No. 930 dtd. 27.02.2019. | 47.28 | 34.78 Supply=17.53 Erection=17.24 | Feb.-2021 | 'Applied |  |  | 1 | 1 | 1
11 |  | 132KV DC line from 132/33KV Phulbani S/S to 132/33KV Boudh S/S | Line: 132KV DC line length - 65.82Kms Substation : 132KV B.E.- 2 nos each at Boudh & Phulbani. | RRCP | NULL | M/s. Sidharth Engg. Ltd. JV M/s.Deepak Cables(I) Ltd., Bangalore-560001. LOI No. Pkg.-25/2015-16-43/2015/3804 (Supply) & 2178(Erection) dt.30.3.16 | 39.36 | 44.98 Supply – 31.79 Cr. Erection -13.18 Cr. | 2018-03-01 | 31.10.2021 |  |  | 1 | 1 | 6
12 |  | 400/220KV Meramundali-B GIS | Substation: TFR Capacity: 2x500MVA,400/220KV 400KV 400KV Linefdr. bay - 8 nos. 400 KV ICT bay - 2 nos 400 KV Tie bay - 5 nos 220KV 220KV Fdr bay- 4 nos. Tfr. Bay – 2 nos. B/C bay – 1 no. | OWN | NULL | M/s SIEMENS LTD. Pkg.-57/2016-17-48/2016/7354 dt.30.12.2017 | 332 | 143.39 Supply :- 122.60 Cr. Erection :- 20.79 Cr. | 2019-06-01 | 31.10.2021 |  |  | 1 | 1 | 6
13 |  | Diversion of one no.400kV Line and 4nos 220kV line with 220kV LILO arrangement for connectivity with 400/220kV GIS Meramundali-B. | Diversion of 400kV Line-01no Diversion of 220kV line with LILO arrangement-4nos UG EHV Cable work for diversion of 220kV line to Meramundali-B. | Own | NULL | M/S A.K.Das Associates Ltd JV with M/S Cable Corporation of India Ltd. W.O No. 1001 dtd. 01.03.2019 | 41.53 | 36.03 Supply :- 27,14 Core. Erection :- 8.88 Core. | 2020-03-01 | 2021-02-28 |  |  | 1 | 1 | 6
14 |  | 220/132/33KV Kiakata S/S with associated 220KV DC line from Katapalli to Kiakata & 132KV DC line from Boudha to Kiakata. | Substation: TFR Capacity: 2x160MVA,220/132KV &1x20MVA, 220/33KV Line: 220KV DC Line - 125Kms. 132KV DC Line – 20Kms. | JICA | NULL | M/s Tata Projects Limited Pkg.-JICA(07-Kiakata & Daspalla)-50/2016/523 dt.29.01.2018 | 156.11 | 160.19 Supply: 101.52 Cr. Erection: 58.66 Cr. | Jan' 2020 | 2021-06-28 |  |  | 1 | 1 | 6
15 |  | Instalation of 3rd 315 MVA, 400/220kV ICT alongwith construction of one no 400kV & one no 220kV Transformer Bay with associated system at existing 400/220kV Grid sub-station New Duburi. | 400 kV DIA 1 Nos 220 kV Transformer Bay 1 No | Own | NULL | M/S A.K.Das Associates Ltd. Work Order No. 3924 & 3929 Dtd. 22.06.2017 of Sr.G.M(CPC), OPTCL. | 29.58 | 13.6 Supply=9.72 Erection=3.87 | March-2019 | 02.02.2022 |  |  | 1 | 1 | 4
16 |  | 220/132/33kV Grid sub-station at Turumunga with associated 220kV line from 400/220kV PGCIL Keonjhar to Turumunga & 132kV LILO line from 132kV Palasapanga-Karanjia SC line. | Sub-station: 220kV bay-07, 100MVA 220/132kV auto-02nos. 132kV bay-05, 20MVA transformer-02nos, 33kV bay-10. 220kV Line-17.248K.Ms 132kV Line-31.713K.Ms. | JICA | NULL | M/S Stelmec LTD.JV with M/S Laxmi Transmission W.O No. 701 Dtd. 18.02.2019 | 119.3 | 103.12 Supply=68.43 Erection=34.69 | Feb.-2021 | 31.3.2022 |  |  | 1 | 1 | 4
17 |  | Construction of 220kV LILO line from one circuit of existing 220kV TTPS-JODA D/C Line (Circuit-II) to 220/33kV GIS Substation, Keonjhar | 220kV LILO line: 14 kms (approx.) | Own | NULL | M/s Empowertrans Pvt. Ltd. W.O. No. 411 Dtd. 03.02.2020 | 29.97 | 12.46 Supply=8.92 Erection=3.54 | Feb.-2021 | 22.09.2021 |  |  | 1 | 1 | 4
18 |  | Construction of 220/132/33kV Grid S/S, Dhamara, Balimunda with associated 220kV LILO line | Substation: Trf Capacity: 2x160 MVA 220/132kV, 2 x 40 MVA 132/33kV 220kV Side: 220kV Feeder bay:02 220kV transformer bay:02 220kV B/C bay:01 132kV Side: 132kV Feeder bay:02 132kV transforemer bay:02 132kV B/C bay:01 33kV Side: 33kV Feeder bay:05 33kV Transformer bay:02 33kV B/C bay:01 | Own | NULL | M/s TATA Projects Ltd. W.O No: 3593 dtd 29.06.2018 | 89.78 | 70.5 Supply=37.52 Erection=32.98 | June.-2020 | 31.08.2021 |  |  | 1 | 1 | 5
19 |  | Construction of 132kV DC line from 132/33kV GIS sub-station Chandbali to 220/132/33kV Grid sub-station, Balimunda(Dhamara) | Line Length-27.237K.Ms Total Towers-106nos | DRPS | NULL | M/S Gupta Power Infrastructures Ltd. W.O no.215 dtd. 17.01.2019 of CGM(CPC). | 18.74 | 18.18 Supply=12.57 Erection=5.61. | July.-2020 | 31.08.2021 |  |  | 1 | 1 | 5
20 |  | 2X20MVA 132/33kV Grid sub-station, Chandipur and associated 132kV LILO line fron 132kV Soro-Balasore line. | 132kV bay-05 33kV bay-07 132kV line-26.42K.Ms | JICA | NULL | M/S STELMEC LTD. W.O No. 701 Dtd. 18.02.2019 of CGM(CPC). | 46.84 | 44.88 Supply=23.17 Erection=21.71 | 2021-02-01 | 7.3.2021 Applied for extension |  |  | 1 | 1 | 5
21 |  | 2x20 MVA, 132/33 KV Sub-station at R.Udaigiri along with associated 132 KV LILO line from 132 KV Mohana to Digapahandi SC line. (36.140Kms.) (Gajapati). | Substation: TFR capacity- 2x20MVA 132KV Bay -4 no. 33KV Bay – 7 no. Line : 36.140Km | 40% Govt | NULL | M/s. SEL JV with M/s. Deepak Cable, Bangalore. W.O. No.5218 & 5223 dt.05.09.2014. | 44.05 | 45.41 Supply=34.71 Erection=10.7 | Mar.-2017 | Upto 31.12.2020 (Project License extension to be applied by agency) |  |  | 1 | 1 | 1
22 |  | 2x20MVA ,220/33KV Grid S/S at Baliguda with associated 220KV Kesinga- Baliguda DC line & 220KV Bay Extns. At Kesinga. | Substation: TFR capacity- 2x20MVA, 220KV Bay -5 no. 33KV Bay – 8 no. 220KV Feeder bay Extn. -2nos. Line : 96.025Km | Own | NULL | M/s. Flowmore Ltd., Ranchi JV M/s Cobra W.O. No.1017 & 1022 dt.11.02.2015 | 98.93 | 115.2 Supply=81.14 Erection=34.06 | June.-2017 | upto 31.12.2018 (Project License extension to be applied by agency) |  |  | 1 | 1 | 1
23 |  | Construction of 2x20 MVA, 220/33 KV Grid S/S,Dasapalla with associated 220 KV LILO line from 220KVKV Bhanjanagar-Meramundali line to proposed S/S(Line length- 31.426Kms.) | Substation: TFR capacity- 2x20MVA , 220/33KV .Line : 31.426Km(LILO arrangement) | JICA | NULL | M/s Tata Projects Limited Pkg.-JICA(07-Kiakata & Daspalla)-50/2016/523 dt.29.01.2018 | 64.08 | 59.26 Supply=35.27 Erection=23.99 | 2020-02-01 | Upto 28.06.2021 (Project License extension to be applied by agency) Division sent a letter to agency for renewal |  |  | 1 | 1 | 1
24 |  | 132kV Parlakhemundi-R.Udayagiri DC line & 132KV Fdr.Bay Extns. | Line : 63.832Km | RRCP | NULL | M/s JDC Infratech Pvt. Ltd, Balasore. W.O. no. dtd.30.03.2018 | 41.82 | 42.08 Supply=26.88 Erection=15.2 | 2020-03-01 | upto 31.03.2021 (Project License extension applied by agency upto 31.03.2022) |  |  | 1 | 1 | 1
25 |  | 220kV DC line from existing 220kV Theruvalli-Narendrapur DC line to 220/132/33kV Grid sub-station Aska along with 2nos 220kV feeder bay extension at Aska. | Line: 220 KV D/C line: 45.15 Kms. 220kV Feeder bay: 2nos. | RRCP | NULL | M/S Gurupreet Galvanising Pvt. Ltd. W.O No.5973 dtd. 04.12.2018 | 42.12 | 39.09 Supply=27.79 Erection=11.30 | 2020-06-01 | upto 29.08.2021 |  |  | 1 | 1 | 1
26 |  | 132/33kV GIS at Hinjilicut | 132KV Side: Feeder Bay-02 Nos. Trf. Bays- 02 Nos Bus coupler - 01 No. 33 KV Side: Fdr bay - 05 nos Trf. Bays- 02 Nos Bus coupler - 01 No. | Own | NULL | M/s GE T&D India Ltd. W.O No. 659 dtd. 14.02.2019 | 45.22 | 28.71 Supply=20.18 Erection=8.53 | 2020-08-01 | upto 31.12.2021 |  |  | 1 | 1 | 1
27 |  | Construction of one no. of 220KV feeder bay with SAS at 220/33KV Grid S/S, Nayagarh with associated 220KV 2-Phse line on 220KV DC Tower from 220/33KV Grid Sub-station, Nayagarh to RTSS at Nayagarh. | 220KV Feeder bay - 1no. |  | NULL | M/S Siddhartha Engineering Limited. NOA No 92 dtd.21.01.2021 of C. G.M (CPC), OPTCL, BBSR. | 20.63 | 13.46 Supply=7.20 Erection=6.26 | 20.09.2022 | Not obtained yet |  |  | 2 | 1 | 2
28 |  | 132KV SC line from 132/33KV grid Chandikhole S/S to proposed RTSS at Dhanmandal with 1 no. 132KV Fdr. Bay extn. at Chandikhole S/S | Length-16.309Kms |  | NULL | M/S Gupta Power Infrastructures Ltd. W.O no.5195 dtd. 10.10.2018 of CGM(CPC). | 12.29 | 11.29 Supply=7.102 Erection=4.27 | Oct-2019 | 30.04.2021 Applied for extension |  |  | 2 | 1 | 3
29 |  | 132KV SC line(2 conductor) from 132/33KV grid Choudwar S/S to proposed RTSS at Charbatia with 1 no. 132KV Fdr. Bay extn. at Choudwar S/S | Length-13.484Kms |  | NULL | M/S Krishna Power Construction (p) Ltd. W.O no.5337 dtd. 22.10.2018 of CGM(CPC). | 13.89 | 11.97 Supply=7.43 Erection=4.88 | 2020-04-01 | 31.03.2022 |  |  | 2 | 1 | 3
30 |  | 132KV SC line(2 conductor) from 220/132/33KV grid Paradeep S/S to proposed RTSS at Siju with 1 no. 132KV Fdr. Bay extn. at Paradeep S/S | Length-14.00K.Ms |  | NULL | M/S A.K.Das Associates Ltd. JV Partner M/s Mascot Electromech Pvt Ltd Work Order No. 3588 Dtd. 29.06.2018 of CGM(CPC), OPTCL. | 9.43 | 14.29 Supply=7.32 Erection=6.96 | 2019-12-01 | 30.4.2021 Applied for extension |  |  | 2 | 1 | 3
31 |  | Diversion of 400kV Meramundali-Duburi D/C line at Loc.no-16/0 to 18/0, 26/0 to 29/0 and 43/0 to 44/0 for new Angul-Sukinda Railway line. | Diversion of 400kV Meramundali-Duburi DC line at Location 16/0 to 18/0, 26/0 to 29/0 & 43/0 to 44/0. Total tower-18nos. |  | NULL | M/S Astavinayak Construction. W.O No. 496 dtd. 27.01.2018 of CGM(CPC). | 31.57 | 14.48 Supply - 9.89 Cr. Erection - 4.59 Cr. | 2019-01-01 | NA |  |  | 2 | 1 | 6
32 |  | 132KV SC line(2 conductor) from 132kV switching statrion at M/S Jabamayee Ferro Alloys Ltd to proposed RTSS at Sukinda with 1 no. 132KV Fdr. Bay extn. at 132kV switching statrion at M/S Jabamayee Ferro Alloys Ltd | Length-3.678Kms |  | NULL | M/S JDC Infratech Pvt. Ltd. W.O no.491 dtd. 27.01.2018 of CGM(CPC). | 14.25 | 6.43 Supply=3.88 Erection=2.55 | Jan'19 | 30.09.2021 |  |  | 2 | 1 | 4
33 |  | 132KV SC line(2 conductor) from 132/33kV Grid S/S Rairangpur to proposed RTSS at Rairangpur with 1 no. 132KV Fdr. Bay extn. at Grid S/S Rairangpur | Length-10.523Kms |  | NULL | M/s Alekh Bharati Constructions Pvt. Ltd., Bomikhal, Bhubaneswar JV Partner M/s ASB Energy Systems & Constructions Pvt. Ltd. W.O. no: 315 dtd. 26.03.2021 of CGM(CPC) | 12.52 | 7.32 Supply=5.05 Erection=2.27 | 25.03.2022 | Not applied by agency yet |  |  | 2 | 1 | 4
34 |  | 132kV DC line (2 phase) from Bangiripoisi S/S to the proposed RTSS at Bhanjpur with 02 nos. of bay extensions at Bangiriposi S/S. | Length-40 kms (approx. |  | NULL | M/s. JDC Infratech Private Limited. W.O. no: 433 dtd. 07.05.2021 of CGM(CPC) | 47.82 | 22.26 Supply=14.44 Erection=7.82 | 06.11.2022 | Not applied by agency yet |  |  | 2 | 1 | 5
35 |  | Const. of 9 (Nine) nos. of river crossing locations by putting 18 nos. of OC+15/UR +6 towers for different existing 33 kV And 11 kV line crossings to get adequate navigational clearance over various rivers for national water ways-5 under KED-I, Kendrapara and KED-II, Marshaghai. | 18 nos. of OC+15/UR+6 towers | Deposite work (CESU) | NULL | M/S Siddhartha Engineering Ltd. Work Order No.SGM-CPC-I-Deposit work(CESU)-(PKG-44/2018-19)-53/2018/986(13), Dtd.01.03.2019 of C. G.M (CPC), OPTCL, Bhubaneswar | 17.97 | 14.86 Supply=4.13 Erection=10.73 | 'Feb-2020 | As it is a CESU work and we are constructing only a part of line, project license is not required. |  |  | 3 | 1 | 3